## Governance
sr_# | name | ssc_reference | module | score | task | subtasks
1 | Board Commitment to Sustainability Standards | Page 7, Para. 3 | Governance | 0 | Receive Board Meeting Minutes/ Resolution Approving the Adoption of Sustainability Standards | 1. Prepare Approval Document;
2. Sustainability Standards and Certification Discussed & Approved in Board Meeting; and
3. File and upload Approval Document.
2 | Purpose Statement** | Page 7, 4.1 to 4.3 & General Requirements Page 8 for Guidelines | Governance | 20 | Get Board Approval for the Purpose Statement | 1. Prepare a list of core active members;
2. Conduct meeting(s) with at least one third of the core active members;
3. Solicit proposals;
4. Shortlist Purpose Statement;
5. Conduct final meeting with the core active members to reach consensus;
6. Document outcome of the meeting;
7. Get Board Approval for the Purpose Statement; and
8. File and upload Board Resolution/ Approval and a Brief Report of the process (which shall include the names of stakeholders involved) to formulate the Purpose Statement.
3 | High Impact Goals | Page 8, 4.4 | Governance | 25 | Get Board Approval for the High Impact Goals | 1. Prepare a list of core active members;
2. Conduct a meeting with the core active members;
3. List all the key interests of the core active members;
4. Based on the list of interests, develop High Impact Goals
5. Solicit proposals;
6. Shortlist High Impact Goals;
7. Conduct final meeting with the core active members to reach consensus;
8. Document outcome of the meeting;
9. Get Board Approval for the High Impact Goals;
10. Set next review date/ period; and
11. File and upload Board Resolution/ Approval and a brief report about the process, which shall include the names of stakeholders involved, to formulate the High Impact Goals.
4 | Audit Report of the Institutional Alignment for the Sustainability Standards | Page 8, 4.4.4 | Governance | 0 | Get Board Approval for the Audit Report | 1. Assign Internal Auditor or nominate an auditor from one of the certified organizations to submit a report on the alignment of all policies, procedures and processes with the Sustainability Standards;
2. Get the Alignment Audit Report reviewed by the Board; and
3. File and upload Audit Report.
5 | Board Composition for Sustainability | Page 9, 4.5 a & 4.6 | Governance | 15 | Create Sustainability Compliant Board | 1. Identify gaps in competency, diversity, knowledge and skills, gender, ethnicity, age and experiences needed to govern a 21st Century value-driven association;
2. In case of substantial gaps, get board approval for its re-composition to create a sustainability compliant board;;
3. Develop and implement conflict of interest policy, and ensure that all the board members sign the Conflict of Interest Statement.
4. Initiate process for creating sustainability compliant board;
5. Finalize new Board composition; and
6. File and uploaded SSCI Compliant Board profile.
6 | Promote & Monitor Innovation Performance | Page 9, 4.5 b to e | Governance | 20 | Create an Innovation Organization | 1. Issue guidelines for promoting culture of innovation;
2. Establish and communicate innovation targets;
3. Encourage and facilitate executives and staff in achieving innovation targets (Optional: Consider creating Innovation Leaders/ Champions);
4. Integrate Innovation Performance in Board agenda;
5. Monitor Innovation Performance;
6. Issue Periodical Innovation Performance Report; and
7. File and upload Innovation Performance Report along with the Documentary Evidence of the Actions undertaken for this task.
7 | Competitive & External Risk Management & Mitigation | Page 9, 4.5 f & g | Governance | 15 | Manage and Mitigate Competitive & Other External Risks | 1. Write short and precise Terms of Reference (e.g. what should the report include/ which information is needed to assess risks arising from external factors.
2. Select and assign suitable person WITHIN the assocation to lead this task of Risk Assessment;
3. Identify suitable Group Members of this task WITHIN the association AND from the core active membership for creating a cross-functional team which will support the development/ update of Risk Assessment;
4. Develop a Report on Risk Assessment;
5. Receive feedback from trusted, committed and relevant core active members;
6. Undertake post-consultation modifications where required;
7. Receive top management approval;
8. Finalize Risk Assessment Report;
9. Discuss the report in Board Meeting and receive approval;
10. Issue Board Guidelines to Manage Risks;
11. Monitor Implementation of Board Guidelines;
12. Issue Periodical Risk Assessment Report;
13. Document all the actions taken for this task; and
14. File and upload Risk Assessment Reports along with the Documentary Evidence of the Actions undertaken for this task.
8 | Long-Termism: Review & Align all the Policies with Organizational Purpose and High Impact Goals | Page 10, 4.7 a & c | Governance | 10 | Integrate Long-Termism Across All Policies | 1. Prepare list of all policies;
2. Review all policies to ensure that they are in harmony with the association's purpose and high impact goals and no part of the policies is a barrier to turn organizational purpose into practice and putting high impact goals into actions;
3. Identify policies (if any) that promote short-term profitability or solutions at the expense of long-term organizational sustainability, exposes the association to undue risks (including reputational risks) or have reasonable potential to cause existential crisis;
4. Take corrective actions where necessary;
5. Set next review date/ period; and
6. Document all the actions taken for this task; and
7. File and upload the Documentary Evidence of the actions undertaken for this task.
9 | Institutional/ Broad-based Ownership of Sustainability Standards | Page 10, 4.7 b | Governance | 0 | Create Organization-Wide Ownership of Sustainability Standards | 1. Run regular programs to brief core active members of the association, board, executives and staff about requirements of becoming and remaining a Sustainability Certified Association;
2. Ensure they understand the implications of sustainability standards on their respective roles and what is expected from them in the future. The discussions shall also include (but not limited to) Purpose Statement, High Impact Goals, Innovation Culture & E & I Policy;
3. Identify Sustainability Leaders/ Champions (or use other title) to ensure that the adaptation of Sustainability Standards is led from WITHIN the association and NOT led by external consultants/ resource persons; and
4. File and upload Documentary Evidence of the Actions undertaken for this task.
10 | Compliance with all Applicable Laws & Regulations | Page 10, 4.7 d | Governance | 10 | Ensure Legal and Regulatory Compliance | Outline all actions to ensure compliance with applicable laws and regulations;
2. Put effective monitoring system in place to detect violation;
3. Ensure disciplinary actions are taken in case of violation of applicable laws and regulation;
4. Ensure that Compliance Officer is easily accessible for any questions from the executive and staff relevant to the issues related to compliance;
5. Periodically prepare Compliance Report; and
6. File and upload the Documentary Evidence of the actions taken for this task.
12 | Ethics & Integrity (E&I) Policy | Page 10, 4.8 | Governance | 10 | Develop and Implement Ethics & Integrity Policy and Monitor its Implementation | 1. Select and assign suitable person WITHIN the association to lead this task of developing/ updating E&I Policy;
2. Identify suitable Group Members of this task WITHIN the assocation AND from the core active membership for creating a cross-functional team which will support the development/ update of E&I Policy;
3. Prepare draft version of the E&I Policy;
4. Receive feedback from internal and trusted, committed and relevant external stakeholders;
5. Undertake post-consultation modifications where required;
6. Receive top management approval;
7. Finalize new/ updated E&I Policy;
8. Discuss the report in Board Meeting and receive approval;
9. Take necessary actions to ensure implementation;
10. Deploy a Monitoring System for ensuring implementation, detecting violation and taking disciplinary actions;
11. Document all the actions taken for this task; and
12. File and upload the E&I Policy along with the Documentary Evidence of the Actions undertaken for this task.

## Management
sr_# | name | ssc_reference | module | score | task | subtasks
1 | Alignment of Senior Executive Positions with the Sustainability Standards | Page 11, 5.1 | Management | 2 | Write Statements and Revise Job Descriptions of All Senior Executive Positions | 1. List all Senior Executive Positions;
2. Consult with each executive as to how his/ her position contributes in achieving the association's Purpose and High Impact Goals;
3. Prepare draft statements in consultation with each Senior Executive;
4. Finalize written statements;
5. Review and modify existing Job Descriptions of all the Senior Executive Positions to align them with the assocation's Purpose and High Impact Goals;
6. Set next review date/ period;
7. Document all the actions taken for this task; and
8. File and upload Written Statements along with the Documentary Evidence of the Actions undertaken for this task.
2 | Alignment of Committees, Departments & Sub-Departments with the Organizational Purpose & High Impact Goals | Page 11, 5.2 | Management | 2 | Write Statements and Revise ToRs of All Committees, Departments & Sub-Departments | 1. List all Committees, Departments & Sub-Departments;
2. Discuss with respective unit as to how it contributes in achieving the association's Purpose and High Impact Goals;
3. Finalize written statements;
4. Review and modify existing ToRs of all the above units to align them with the association's Purpose and High Impact Goals;
5. Set next review date/ period;
6. Document all the actions taken for this task; and
7. File and upload Written Statements and Documentary Evidence of the above actions.
3 | Alignment of Policies, Procedures & Processes with the Organizational Purpose & High Impact Goals | Page 11, 5.3 a | Management | 2 | Modify Policies, Procedures and Processes | 1. Prepare list of all policies, procedures and processes;
2. Prepare documents for the Board and take necessary actions to enable alignment of all policies with the association Purpose and the High Impact Goals;
3. Review and modify all procedures and processes to ensure that they are in harmony with the association purpose and high impact goals and no part of the procedures and processes is a barrier to turn organizational purpose into practice and putting High Impact Goals into actions;
4. Set next review date/ period;
5. Document all the actions taken for this task: and
6. File and upload Documentary Evidence of the actions undertaken for this task.
4 | Turning Organizational Purpose & High Impact Goals into Actions | Page 11, 5.3 b & c | Management | 2 | Link Performance with Purpose and High Impact Goals | 1. List all executives, key and relevant staff members, committees, departments and key sub-departments;
2. Cascade High Impact Goals across the above positions and units;
3. Set sub-goals and indicators for each of the above for linking performance of the above position holders and units with their required contributions to the association's Purpose and High Impact Goals;
4. Set next review date/ period;
5. Document all the actions taken for this task; and
6. File and upload Documentary Evidence of the actions undertaken for this task.
5 | Alignment of Internal Reporting with High Impact Goals | Page 11, 5.3 d | Management | 1 | Link Reporting to High Impact Goals | 1. Prepare a list of all key internal reports;
2. Review and modify the reporting structures and formats (or templates) for establishing a link between the matters reported and the High Impact Goals and facilitating easy tracking of the progress towards those goals;
3. Deploy new reporting structures and formats (or templates) for all key internal reports;
4. Set next review date/ period;
5. Document all the actions taken for this task; and
6. File and upload Documentary Evidence of the actions undertaken for this task.
6 | Ensure Purpose - Driven Organizational Performance through Gap Audit | Page 11, 5.4 | Management | 1 | Deliver Gap Audit and Corrective Action Report | 1. Select and assign a suitable person WITHIN the association to periodically conduct the Gap Audit to identify inconsistencies between departmental / unit-wise goals, practices, policies, procedures and processes and their association's purpose and high impact goals;
2. Create a Gap Audit Report;
3. Get the report reviewed by the Management;
4. Set next review date/ period;
5. Document all the actions taken for this task; and
6. File and upload Gap Audit and Corrective Actions Report.
7 | Develop an Innovation Strategy | Page 11, 5.5 a | Management | 5 | Deliver Written Innovation Strategy | 1. Select and assign a suitable senior position holder WITHIN the association to lead Corporate Innovation;
2. Identify suitable executives and staff WITHIN the association and from core active members for creating cross-functional team and consider open innovation (engaging core active members to enable flow of ideas from outside to the association);
3. Prepare draft innovation strategy;
4. Receive feedback from internal and trusted and committed core active members;
5. Undertake post-consultation modifications where required;
6. Receive top management commitment;
7. Deliver Innovation Strategy;
8. Set next review date/ period; and
9. Document all the actions taken for this task; and
10. File and upload Innovation Strategy and Documentary Evidence of the actions undertaken for this task.
8 | Foster Innovation Environment (Responsibility: Corporate Innovation Leader) | Page 11, 5.5 b Page 12, 5.5. c to e | Management | 5 | Create a Culture of Innovation | 1. Take steps for enabling generation, experimentation and scaling up of ideas;
2. Check that new ideas lead to achieving the association's Purpose and the High Impact Goals;
3. Ensure that cross-functional innovation team has diversified skill sets, knowledge, experiences, gender balance and represents different age groups and ethnical backgrounds;
4. Ensure C-Level commitment to innovation;
5. Take steps to inspire and engage employees and external stakeholders in the organization’s innovation journey;
6. Set next review date/ period;
7. Document all the actions taken for this task; and
8. File and upload the Documentary Evidence of the actions undertaken for this task.
10 | Enhance Financial Performance | Page 12, 5.7 | Management | 40 | Deliver Short Report | 1. Report Specific Actions Taken to Improve: Debt, Current, Quick & Operating Ratios.
2. File and upload the Short Report.
11 | Drive Future Performance | Page 12 (5.7), 13 (General Requirements and Guidelines) | Management | 65 | Introduce/ Update Non-Financial Metrics | 1. Select and assign a suitable senior position holder WITHIN the organization to lead the task of developing Non-Financial Performance Metrics;
2. Identify suitable executives and staff WITHIN the association and from core active members for creating cross-functional team which will develop/ update Non-Financial Performance Metrics;
3. Prepare draft version of Non-Financial Performance Metrics;
4. Receive feedback from internal stakeholders and trusted, committed and relevant core members;
5. Undertake post-consultation modifications where required;
6. Document top management approval;
7. Get Board approval;
7. Introduce/ Update Non-Financial Metrics;
8. Set next review date/ period;
9. Document all the actions taken for this task; and
10. File and upload latest Non-Financial Performance Metrics and Documentary Evidence of the actions undertaken for this task.

## Business Model
sr_# | name | ssc_reference | module | score | task | subtasks
1 | Business Modelling and Analysis | Page 14, 6.1 & Page 15 | Business Model | 65 | Developing, Modifying and Validating the Business Model(s) | 1. Select and assign a suitable senior position holder WITHIN the assocation OR the relevant Board Committee to lead the task of Developing/ Modifying and Validating the Business Model(s);
2. Identify and select suitable Group Members of this task WITHIN the association and from the core active members for creating a cross-functional team who will support the Development/ Modification and Validation of Business Model(s);
3. Propose additions, modifications or replacement with new business model(s) to ensure alignment between business model(s) and the organizational purpose and high impact goals;
5. Prepare draft Business Model(s) Evaluation and Recommendation Report;
6. Receive feedback from internal stakeholders and trusted, committed and relevant core members;;
7. Undertake post-consultation modifications where required;
8. Receive Top Management approval;
9. Finalize Modifications, Validations or Development of New Business Model(s);
10. Document top management approval
11. Receive Board approval;
12. Begin Implementation;
13. Set next review date/ period;
14. Document all the actions taken for this task; and
15. File and upload the Report on Modifications, Validations or Development of New Business Model(s) along with the actions undertaken for this task.
2 | Manage Externalities | Page 15, 6.2 | Business Model | 60 | Monitoring Impact of External Factors on the Organization's Business Model(s) | 1. Select and assign a suitable senior position holder WITHIN the assocation to lead the task of Monitoring Externalities;
2. Identify suitable Group Members of this task WITHIN the association and from the core active members for creating a cross-functional team who will support fulfilling this task:
3. Analyze the external factors with reasonabe potential of impacting the business model(s) and recommend actions;
4. Prepare draft version of the Report on Monitoring Impact of External Factors on the Association's Business Model(s) and Recommendations;
5. Receive feedback from internal stakeholders and trusted, committed and relevant core members;
6. Undertake post-consultation modifications where required;
7. Document top management approval;
9. Get the Board approval;
10. Set next review date/ period;
11. Document all the actions taken for this task; and
12. File and upload the Monitoring and Recommendations Report along with the Documentary Evidence of the actions undertaken for this task.

## Operations
sr_# | name | ssc_reference | module | score | task | subtasks
1 | Optimal Utilization of Human, Financial and Physical Resources | Page 16 and 17 (Guidelines) | Operations | 85 | Achieving Operational Excellence | 1. Simplify, streamline and optimize the processes, end-to-end;
2. Simplify, streamline and optimize organizational structure and align it with the high impact goals;
3. Segregate repetitive and low-value tasks from knowledge-centric, skill-based and high-value tasks;
4. Reduce and automate repetitive and low-value tasks;
5. Focus on knowledge-centric, skill-based and high-value tasks;
6. Promote cross-function teams and collaborative work-place environment;
7. Identify and eliminate organizational silos and duplication of processes;
8. Substantially reduce ecological footprint both within the applicant institution and its supply chain;
9. Document top management approval for each of the task modified or proposed to be eliminated;
10. Get Board approval where required;
11. Begin Implementation;
12. Set next review date/ period;
13. Document all the actions taken for this task; and
14. File and upload the Documentary Evidence of the actions undertaken for this task.
2 | Audit Report on the Operational Excellence | Page 16 | Operations | 40 | Deliver Audit Report | 1. Select and assign a suitable person WITHIN the organization to periodically conduct the Operational Audit;
2. Create an Operational Audit Report;
3. Get the report reviewed by the Management;
4. Submit the Final Operational Audit Report to the Board;
5. Set next review date/ period;
6. Document all the actions taken for this task; and
7. File and upload Operation Audit Report.

## Products
sr_# | name | ssc_reference | module | score | task | subtasks
1 | Align Products with the High Impact Goals and Ensure their Responiveness to Technological Developments and Changing Customer Preferences and Regulatory Environment | Align Products with the High Impact Goals and Ensure their Responiveness to Technological Developments and Changing Customer Preferences and Regulatory Environment | Products | 75 | Develop and Execute a Robust Product Portfolio Management System (PPMS) | 1. Select and assign a suitable senior position holder WITHIN the assocation to lead the task of Product Portfolio Management System (PPMS);
2. Identify suitable Group Members of this task WITHIN the assocation and from the relevant Board Committee or core membership who will support the Development of the PPMS;
3. Prepare a list of all products, their key features and member benefits, rank the products according to the role they play in achieving the high-impact goals and mark value creators and value destroyers;
4. Take actions to discontinue value-destroyers. These are the products that harm the long-term interest of the association and its core members
5. Take actions to simplify design and delivery of the products which are value creators, while putting the needs and interests of the core members at the centre of the product portfolio management strategy;
6. Ensure that the product portfolio is fully aligned with the High-Impact Goals;
7. Put a system in place to collect accurate, reliable, timely, relevant and complete data of the performance of the product portfolio;
8. Establish a process of new product development. The stages of the process shall encompass idea generation to market-testing and post-launch review
9. Based on the above, prepare draft version of PPMS;
10. Receive feedback from internal stakeholders and trusted, committed and relevant core members;
11. Undertake post-consultation modifications where required;
6. Document Top Management approval;
12.Get Board approval;
13. Implement/ Update PPMS;
14. Set next review date/ period;
16. File and upload latest PPMS along with the Documentary Evidence of the actions undertaken for this task.
2 | Conduct Product Portfolio Audit | Page 20, 8.7 | Products | 50 | Deliver Product Portfolio Audit Report | 1. Select and assign a suitable person WITHIN the organization to periodically conduct the Product Portfolio Audit;
2. Create a Product Portfolio Audit Report;
3. Get the report reviewed by the Management;
4. Submit the Final Product Portfolio Audit Report to the Board;
5. Set next review date/ period;
6. Document all the actions taken for this task; and
7. File and upload Product Portfolio Audit Report.

## Technology
sr_# | name | ssc_reference | module | score | task | subtasks
1 | Internal Digitization | Page 20, 9.1.1 | Technology | 65 | Deliver an Action Plan for Digitization of Operations | 1. Select and assign a suitable senior position holder WITHIN the association to lead the task of developing/ updating an Action Plan for Digitizing Operations;
2. Identify and select suitable Group Members of this task WITHIN the assocation and from the relevant Board Committee or core membership who will support the development/ update of action plan;
3. Prepare draft version of the Action Plan;
4. Receive feedback from internal and trusted, committed and relevant core members;
5. Undertake post-consultation modifications where required;
6. Document top management approval;
8. Get Board approval
7. Finalize Action Plan;
8. Set next review date/ period;
9. Document all the actions taken for this task; and
10. File and upload the latest Action Plan for Digitizing Operations along with the Documentary Evidence of the actions undertaken for this task.
2 | Organization's Positioning in a Digital Economy | Page 20, 9.1.2 | Technology | 60 | Deliver an Action Plan for Organization's Positioning in a Digital Economy | 1. Select and assign a suitable senior position holder WITHIN the assocation to lead the task of developing/ updating an Action Plan for Association's Positioning in a Digital Economy;
2. Identify and select suitable Group Members of this task WITHIN the assocation and from the relevant Board Committee or core membership who will support the development/ update of action plan;
3. Prepare draft version of the Action Plan;
4. Receive feedback from internal stakeholders and trusted, committed and relevant core members;
5. Undertake post-consultation modifications where required;
6. Document top management approval;
7. Finalize Action Plan;
8. Set next review date/ period;
9. Document all the actions taken for this task; and
10. File and upload the latest Action Plan for Organization's Positioning in a Digital Economy along with the Documentary Evidence of the actions undertaken for this task.

## Stakeholders Relations
sr_# | name | ssc_reference | module | score | task | subtasks
1 | Create Trust, Confidence and Emotional Bond with the Stakeholders | Page 21 to 23 | Stakeholders Relations | 85 | Develop and Execute a Stakeholder Management Plan (SMP) | 1. Select and assign a suitable senior position holder WITHIN the organization to lead the task of Developing a Stakeholder Management Plan;
2. Identify and select suitable Group Members of this task WITHIN the assocation and from the relevant Board Committee or core membership who will support the Development of SMP;
3. Prepare a list of all stakeholders, key benefits they provide to the core members, rank the stakeholders according to the role they play in achieving the high-impact goals and mark value creators and value destroyers;
4. Strategize management of the value destroyers. Note: Value destroyers are those stakeholders that are not conducive for achieving high-impact goals, and harm the long-term interest of the association and its core members. Therefore, it is necessary that their influence on the activities is eliminated so that the interest of the association and its core members is not compromised;
5. List steps needed to boost cooperation with value creators with the aim to achieve high impact goals;
6. Align Stakeholder Portfolio with the High-Impact Goals and list steps needed to discontinue relationship with those stakeholders that are in conflict with the Purpose Statement and High Impact Goals. In case where it is not possible to discontinue the relationship for strategic reasons, list specific steps necessary to reduce the cooperation to bare minimum and only to the extent that it is not in conflict with the purpose statement and high impact goals of the association;
7. List actions for regularly engaging and communicating with the stakeholders, analysing the outcome of stakeholder management, and taking timely actions to ensure desired results.
10. Based on the above, prepare draft version of the SMP;
4. Receive feedback from internal stakeholders and trusted, committed and relevant core members;
5. Undertake post-consultation modifications where required;
6. Finalize SMP;
7. Document top management approval;
7. Get Board approval;
8. Set next review date/ period;
9. Begin execution of the plan;
10. Document all the actions taken for this task; and
15. File and upload the SMP along with the Documentary Evidence of the actions undertaken for this task.
2 | Generate SMP Report | Page 23, 10.7 | Stakeholders Relations | 40 | Submit, at least twice a year, SMP Report to the Board of Directors. | 1. Select and assign a suitable person WITHIN the organization to periodically write the SMP Report;
2. Create a SMP Report;
3. Get the report reviewed by the Management;
4. Submit the Final SMP Report to the Board;
5. Set next review date/ period;
6. Document all the actions taken for this task; and
7. File and upload the latest SMP Report.

## Human Capital
sr_# | name | ssc_reference | module | score | task | subtasks
1 | Linking Innovation and Human Capital Management for Achieving High Impact Goals | Page 24, 11.1 a to f & 11.2 g | Human Capital | 40 | Create Conducive Environment for Innovation | 1. Regularly conduct ideation sessions;
2. Introduce a process of knowledge creation and sharing;
3. Simplify the process of collecting, analyzing, approving and implementing ideas;
4. Allow experimentation and recognize failures as pillars of creativity and innovation;
5. Create an environment for empowerment in which executives do not micromanage, but encourage their subordinates to take responsibilities and welcome ideas which can contribute in enhancing performance;
6. Provide non-monetary rewards and incentives for creativity and innovation;
7. Promote cross-pollination of ideas by fostering diversity in teams and in workplace - for example diversity in terms of age, gender, culture, ethnic and educational backgrounds, skills and experiences, and in particular by building cross-function teams;
8. Set next date/ period to review the steps taken to create a conducive environment for innovation;
9. Document all the actions taken for this task; and
10. File and upload Documentary Evidence of the above actions
2 | Alignment of Recruiting with the High Impact Goals | Page 24, 11.2 a | Human Capital | 8 | Revise Recruitment Policy | 1. Review recruitment and selection policy and any other relevant documents and propose ammendments to align the policy with the organizational Purpose and High Impact Goals;
2. Discuss proposed ammendments with relevant member(s) of the top management and where necessary with the board members;
3. Incorporate approved changes and release a new Recruitment Policy;
4. Document top management approval;
5. Get Board approval;
5. Set next review date/ period;
6. Document all the actions taken for this task; and
7. File and upload Revised Recruitment Policy.
3 | Alignment of Job Descriptions and HR Decisions with the Organizational Purpose and High Impact Goals | Page 24, 11.2 b & c | Human Capital | 8 | Revise the job descriptions, performance expectations and appraisals, transfers, promotions, compensations and benefits | 1. Select and assign a suitable person WITHIN the organization to lead the Alignment of Job Descriptions and HR Decisions with the Organizational Purpose and High Impact Goals;
2. Identify and select suitable Group Members of this task WITHIN the assocation and from the relevant Board Committee or core membership who will support the revision of Job Descriptions and HR Decision Criteria;
3. Analyze gaps in the alignment of talents available with the association’s organizational purpose and high impact goals;
4. Develop a Report on the Alignment of Job Descriptions and HR Decisions with the Organizational Purpose and High Impact Goals;
5. Hold consultations wtih the Group Members;
6. Undertake post-consultation modifications where required;
7. Finalize report stating current talent pool and talent gap (if any), revised job descriptions and HR Decision Criteria and receive necessary approvals;
8. Document top management approval;
9. Receive Top Management approval;
10. Take necessary actions to ensure implementation of the above decisions;
9. Set next review date/ period;
10. Document all the actions taken for this task: and
11. File and upload Documentary Evidence of the above actions.
4 | Knowledge sharing to Achieve Organizational Purpose and High Impact Goals | Page 24, 11.2 d | Human Capital | 8 | Create a pool of in-house Moderators/ Facilitators for enabling continuous learning and promoting cross-training programs | 1. Identify areas in which in-house moderating and facilitating of learning and knowledge-sharing shall be considered mandatory. These shall include (but not limited to) educating employees about the Organizational Purpose, High Impact Goals, E&I policy, Non-Financial Metrics, Action Plan for Organization's Positioning in a Digital Economy, Organization’s Business Model(s), Member Benefits, and Stakeholder Management Plan (SMP);
2. Prepare a list of potential Master Moderators/ Facilitators for the above and any other areas considered mandatory for in-house moderation/ facilitation;
3. Finalize a list of Master Moderators/ Facilitators according to their expertise and background in the above areas and for conducting cross-training programs;
4. Provide support to Master Moderators/ Facilitators in generating purpose of each of their moderation/ facilitation and knowledge sharing programs and developing any required material (e.g. documents, presentations and equipment);
5. Prepare a list of potential Moderators/ Facilitators to be attached to the Master Moderators/ Facilitators;
6. Finalize a list of Moderators/ Facilitators;
7. Ensure that the number of Moderators/ Facilitators match the organizational size and the pool is diversified in terms of skills, knowledge, experiences, talent, seniority, ethnic background and age;
8. Finalize preparations for launching in-house continuous learning programs fully aligned with the organization’s Purpose and High Impact Goals;
9. Prepare half-yearly knowledge sharing program;
10. Host a Launching Ceremony attended by the President/ CEO and Board Chairperson to formally INSPIRE, ENGAGE, EDUCATE & EXCITE the employees for collectively learning and working to acheive the organization’s Purpose and High Impact Goals;
4. Set next review date/ period;
5. Document all the actions taken for this task; and
6. File and upload Documentary Evidence of the actions undertaken for this task.
5 | Ensure Equal Opportunities for All | Page 24, 11.2 e & f | Human Capital | 8 | Develop/ Update and Implement Equal Opportunities Policy | 1. Select and assign a suitable person WITHIN the organization to lead the development/ update of Equal Opportunities Policy (EOP);
2. Identify and select suitable Group Members of this task WITHIN the assocation and from the relevant Board Committee or core membership who will support the Development/ Update of (EOP);
3. Prepare draft version of the EOP which also promotes inclusion and equity in the workplace, where every executive and staff member are respected and valued, irrespective of their age, gender, ethnicity, disability, belief or any other such factor;
4. Receive feedback from internal and trusted and committed external stakeholders;
5. Conduct consultation sessions;
6. Undertake post-consultation modifications where required;
7. Finalize new/ updated EOP;
8. Receive Top Management approval;
8. Receive Board approval;
9. Take necessary actions to ensure implementation;
10. Deploy a Monitoring System for ensuring implementation, detecting violation and taking disciplinary actions against those who violate the EOP;
11. Set next review date/ period; and
12. Document all the actions taken for this task; and
13. File and upload latest EOP along with the Documentary Evidence of the actions undertaken for this task.
6 | Health of Employees as Organizational Responsbility | Page 25, 11.3 | Human Capital | 45 | Offer HR Well-Being Programs | 1. Organize physical health fitness program;
2. Provide support for managing disabilities;
3. Ensure availability of mental and emotional health fitness program, such as for stress management, conflict resolution and time management;
4. Support personal financial management;
5. Set next review date/ period to assess progress on the HR Well-Being Programs;
6. Document all the actions taken for this task; and
7. File and upload Documentary Evidence of the actions undertaken for this task.
7 | Gain Trust of Employees | Page 25, 11.4 | Human Capital | 8 | Protect Information of Employees | 1. Take steps to guarantee complete confidentiality and discretion in dealing with physical and mental fitness issues of all its employees;
2. Set next date/ period to review the steps;
3. Document all the actions taken for this task; and
4. File and upload Documentary Evidence of the actions undertaken for this task.